## 6 mo. update Oct 2021
Name of FIP | NAPA Policy FIP for the MarinTrust Fisheries Improver Programme – NE Atlantic Blue whiting
Organization: | North Atlantic Pelagic Advocacy Group (NAPA)
Date: | 2022-04-21
Active action and indicators associated w/ action | Tasks | Update October 2021 | Name of file attached (Please attach any relevant document) | Questions/notes
1. Engagement to Ensure Robust Harvest Strategies Adopted and Implemented | Lobby all parties in seeking a joint solution within the framework of a long-term management plan highlighting market consequences of inaction. Lead: NAPA Due date: August 2021 | 1. NAPA produced an op-ed for the MSC to publish in Iceland & Norway. Was published in several outlets in November 21. 2. NAPA presented on our work, and our asks, at ArcticCircle 2021 (1400 participants) on a panel coordinated by the MSC. Received coverage in the Icelandic press. 3. Engagement Resource Pack provided to all Partners in advance of the Coastal States Sharing Discussions 4. 23 Sourcing Statement received from Partners 5. Individual letters sent to each Coastal State fishing minister | 1a. Fishing Daily: https://thefishingdaily.com/latest-news/business-calls-for-sea-change-in-pelagics-management-opinion-piece-by-gisli-gislason/ 1b. Intrafish: https://www.intrafish.com/sustainability/it-is-inexcusable-marine-stewardship-council-blasts-politicians-for-failure-to-agree-on-pelagic-quotas/2-1-1092332 1c. FishFocus: https://fishfocus.co.uk/business-calls-for-sea-change-in-pelagics-management/ 1d. The Nation (a free daily norweigian newspaper): https://www.nationen.no/motkultur/debatt/kvote-krangel-koster/ 1e. Fiskifrettir: https://fiskifrettir.is/frettir/urbota-er-thorf/171490/ 2a. Arctic Circle 2021 Program (see page 37) https://prismic-io.s3.amazonaws.com/arctic-circle-www/10ee58cc-4096-4782-87d0-6559b86501da_Program_2021.pdf 2b. https://www.mbl.is/200milur/frettir/2021/10/15/hota_thvingunaradgerdum_ad_loknum_thremur_arum/ 3. Engagement Resource Pack [attachment] 4. https://www.seafish.org/document/?id=3352bee2-34c1-4eae-986f-aa7c8ab8f122 5 CS Letters [Attached]
| During negotiations for TACs and sharing arrangements, arrange meetings with catching sector (“roundtable”) to encourage a management solution. Lead: NAPA Due date: August 2022 | 1. Third catching sector roundtable was held on 30th March 22. 23 pelagic fishing organisations were invited (from all 7 coastal states) and 8 organisations attended from Denmark, Norway, Sweden, Ireland, Netherlands and Iceland. 2. Aldi Sud presented at the Roundtable - noting the importance for them to see the management of the fisheries improved. | 1. Catching Sector Roundtable Slides [attachment] 2. https://twitter.com/NAPAfisheries/status/1509152503346118664?s=20&t=p_0s2nbedcIcLJxkYzd4Vg
| Communication to continue with Coastal States representatives to promote adherence to exploitation levels consistent with meeting the requirements of Principle 1. Lead: NAPA Due date: April 2024 | 1. Coastal States meeting (October 21) concluded with agreement to follow ICES scientific advice when setting TACs for the three species. 2. Lack of sharing arrangements was recognised as a concerning factor, as was current levels of overfishing. 3. Three Coastal State working groups have been established to create or update reports on the spatial distribution for each stock - could be used as an evidence base for zonal attachment. 4. The sharing agreements meetings scheduled for early 2022. 5. The NEAFC meeting took place in November 22. Measures were adopted for mackerel, blue whiting and ASH in the NEAFC Regulatory Area (international waters) in 2022. 6. Traditional NEAFC catch level for blue whiting for the Russian Federation and Greenland (7.69%) ratified. 7. Concernds were raised by several delegatations. The UK made a general comment on the 3 main pelagic stocks, underlining its concern at their state, as well as on the level of uptake in international waters. Denmark (in respect of the Faroe Islands and Greenland) concurred on the need to exert all efforts on finding a solution on allocations to avoid reflecting badly on the regional processes. Several Parties also underlined their concern about the fisheries. 8. NAPA made opening statement at NEAFC calling for delegates to follow the advice, employ Management Plans and address allocations. 9. Following NEAFC we released a statement entitled "De-coding the coastal States" 10. In advance of the sharing discussions several Coastal states published allocations. This was extremely unhelpful and NAPA published a statement criticizing these unhelpful actions. Picked up in trade press. 11. The initial sharing discussion meeting took place in March 22. NAPA was invited to participate in the plenary. 12. In advance of this meeting we held meetings with the UK, Iceland, Greenland and Russia delegations. At these meetings we expressed our concerns and iterated our asks. | 1-4. Summary from EU: https://ec.europa.eu/oceans-and-fisheries/news/north-east-atlantic-coastal-states-reach-agreement-mackerel-blue-whiting-and-atlanto-scandian-2021-10-28_en 5-7. https://www.neafc.org/system/files/Report%20AM_2021%20Final.pdf 8. https://www.neafc.org/system/files/AM_2021-60_NAPA-NEAFC-Opening-Statement-21.pdf 9. https://www.seafish.org/document/?id=170846d5-5e00-4aa6-9071-dd78f02a8513 10a. Pre-meeting allocations [attachment] 10b. NAPA Statement https://www.seafish.org/document/?id=427b1202-ec5c-4efe-9279-c62cc8256000 10c. Undercurrent: https://www.undercurrentnews.com/2022/01/25/napa-concerned-some-pelagics-quotas-have-been-set-before-sharing-talks-even-begin/ 10d. The Skipper: https://theskipper.ie/pelagic-trade-warns-coastal-states-over-increased-catch-levels/ 10e. The Grocer: https://www.thegrocer.co.uk/fish/north-atlantic-overfishing-retailers-warn-of-possible-boycotts/663806.article 12. These meetings were via Zoom and unminuted. However, the emails setting up the calls/follow-ups are attached.
2. Dispute settlement legal framework and consultation processes | NAPA reviews and produces a document summarizing the coastal states’ and NEAFC’s dispute settlement protocols. Lead: NAPA Due date: August 2021 | 1. Options paper was produced and converted into a position paper wich was used in advocacy. 2. Paper was circulated to all Coastal States. Responses received from UK (Minister & Civil Service) and Iceland. 3. Press Statement was published 4. Position paper was covered in trade press | 1. NAPA position Paper: https://www.seafish.org/document/?id=c57abcb9-c1a8-4455-ab7e-f5a3bd1932fc 2a. UK Minister response [attachment] 2b. UK Defra response was via unminuted phone conversation on 17th March 2c. Iceland response [attachment] 3. Press Statement: https://www.seafish.org/document/?id=92e68743-6de8-431d-97d0-419744113937 4a. FishFocus: https://fishfocus.co.uk/after-a-decade-of-deadlock-its-time-to-seek-help/ 4b. The Fishing Daily: https://thefishingdaily.com/featured-news/after-a-decade-of-deadlock-its-time-to-seek-help-napa-issues-position-paper/ 4c. Undercurrent: https://www.undercurrentnews.com/2022/03/07/retailers-propose-concrete-actions-for-north-atlantic-pelagic-management/
| Lobby a coastal state (i.e. UK) to initiate negotiations for a mechanism, for cooperation and dispute resolution between the Coastal States which is effective in agreeing an appropriate management mechanism consistent with the management plan. Lead: NAPA Due date: August 2023 | 1. During meetings with UK Government on 21st January & 17th March we raised the issue of UK championing the use of the NEAFC dispute mechansim, and for the adoption of a dispute resolution mechanism at the Coastal States meetings. UK remain interested, but no definite agreement though. 2. During meeting with Iceland on 7th Jan we raised the issue of Iceland championing the use of the NEAFC dispute mechansim, and for the adoption of a dispute resolution mechanism at the Coastal States meetings. Iceland were lukewarm - felt it would be incredibly difficult to get agreement.
3. Effective decision-making processes | During negotiations for TACs and sharing arrangements, arrange meetings with catching sector (“roundtable”) to encourage a more precautionary management solution for 2022. Lead: NAPA Due date: August 2022 | 1. Danish Pelagic Producer Organisations wrote letter of support for the blue whiting FIP | 1. Attached.
| Communication to continue with Coastal States representatives to promote responsive and precautionary decision-making, particularly regarding TACs. Lead: NAPA Due date: August 2024 | 1. In advance of the Coastal States sharing discussions NAPA published (Dec 21) a social media short film. As of 20th April, this film has received 834 views on Twitter. 2. In January 22 NAPA published a press statement noting global importance of the fisheries highlighting our first African member (Woolworths SA). This was picked up by the trade press. 3. This was followed in March with another press statement noting NAPA had been joineds bymembers from Canada, Italy and Australia.This was picked up by the trade press. 4. Following outcry over the spillage of 100,000 tonnes of blue whiting, we used the press interest to note that this was approx. 18t whereas over 300,000t were deliberately overfished each year. Was picked up by the national press. 5. The Coastal States sharing discussions took place in February 22 and for the first time a summary of the meeting was published. Following the meeting, we met with the WG chairs who informed us that thew meeting mood was different – no blockers, positive, constructive attitudes; there was a real appetite to reach a 2022 agreement – but may be 2023; the post-meeting statement stimulated in part by NAPA advocacy; there is hope to reach agreement late May/June – may be September; difficulty is the different fishing season start dates for each Coastal State throughout the year (hence 2023 may be more likely). UK & Faroes to attend NAPA Partner meeting on 26th April in their roles as WG Chairs. | 1. https://twitter.com/NAPAfisheries/status/1470316338166050816?s=20&t=-2b8Wu5yPyzwUYCDagM8LA 2a. Press statement https://www.seafish.org/document/?id=dbec02ee-5bc1-41d8-94ad-ed0523a90fed 2b. Undercurrent: https://www.undercurrentnews.com/2021/11/10/napa-announces-first-african-firm-to-join-coalition/ 2c. Fishfocus: https://fishfocus.co.uk/africa-responds-to-napas-call-for-sustainability/ 2d. Fishing Daily: https://thefishingdaily.com/europe-fishing-industry-blog/africa-responds-to-napa-call-for-sustainability-in-northeast-atlantic-pelagic-fisheries/ 2e. Fiskerforum: https://fiskerforum.com/sa-retailer-joins-napa-call-for-sustainable-pelagic-fisheries/ 3a. Press Statement: https://www.seafish.org/document/?id=512f135e-749e-49d4-b93f-fdff3753b7d7 3b. SeafoodSource: https://www.seafoodsource.com/news/premium/environment-sustainability/bolton-group-simplot-ocean-brands-calls-for-sustainable-pelagic-fisheries 3c. EFA News: https://www.efanews.eu/en/item/24386-sustainable-fishing-bolton-group-s-food-business-unit-enters-in-napa.html 3d. Fishing Daily: https://thefishingdaily.com/latest-news/napa-chain-grows-as-three-new-organisations-join-the-pelagics-group/ 3e. FishFocus: https://fishfocus.co.uk/global-supply-chain-unites-in-support-of-sustainable-northeast-atlantic-pelagics/ 3f. Fiskerforum: https://fiskerforum.com/major-names-add-weight-to-napa-membership/ 4a. Press statement https://www.seafish.org/document/?id=e8a97fce-4424-45fa-9b6a-0b44351100bd 4b. Express coverage: https://www.express.co.uk/news/uk/1566943/UK-fishing-news-government-fishing-quotas-NAPA-EU-fishing-UK-water 4c. FishFocus https://fishfocus.co.uk/spillage-of-100-000-blue-whiting-a-drop-in-the-ocean/ 5. https://www.gov.uk/government/publications/fisheries-blue-whiting-herring-and-mackerel-management-in-the-north-east-atlantic-for-2022/chairs-joint-report-of-the-february-2022-consultations
4. Ensure KDE information is collected on vessels supplying MarinTrust factories | By year 3 ensure KDEs for wholefish are – fishing vessel(s), species, catch area and date of landing Lead: NAPA Due Date: June 2024 | TO DO
NOTE: Every NAPA press piece is distributed to over 2,500 media contacts across 33 countries, including all Coastal States, ensuring NAPA’s messages are disseminated to those who need to hear them most.
NOTE: NAPA Was called out in the North American Seafood Expo magazine in March as "driving real change through innovation.” See page 68 https://issuu.com/divcomm/docs/wf_954369_ss22_expo_today_boston-issuu?fr=sOThjZDc4MzUwMg