## Progress report
Initial actions | Completed by | Reviewer’s comments | Actions taken with regard to reviewer comments
Action 1.1 Consult and propose DARD BRVT and Sub-DOF a management plan for trawl fishery in BRVT. 1.1.1 Assessment about status of trawl fisheries management in BRVT 1.1.2 Present and discuss with Sub-DOF about results of the assessment and actions 1.1.3 Consultation workshops with key stakeholders 1.1.4 Develop trawl fisheries management plan based on outputs of 1.1.2 and 1.1.3 1.1.5 Propose to Sub-DOF to incorporate the trawl fisheries management plan into the provincial master management plan of BRVT fishery. | 2022-12-01 | 1. It is not clear what this action covers. Only allocated USD10,000 and is due to be completed by December 2022. 2. Developing a Fisheries Management Plan that has the support of the Sub-DOF and key stakeholders will take at least one year and a budget closer to USD100,000. 3. Not specify what is to be covered in the Fisheries Management Plan. 4. The plan should not only cover fishery resources and fishers but also include plans relating to critical habitats, endangered, threatened and protected (ETP) species and ecosystem structure and function | 1. Revise the deliverable and activities using co-management approach. 2. Reallocate budget. Attachment: Revised FAP
Action 1.2 Propose a mechanism with DARD, Sub-DOF BRVT and BRVT Port authorities for sharing information about fisheries in BRVT. 1.2.1 Mapping fisheries information owners/sources 1.2.2 Dialogues about ways to share information 1.2.3 Develop a fishery database for trawl fisheries and fisheries related activities in BRVT 1.2.4 Consultation workshops with stakeholders 1.2.5 Finalise fisheries database for BRVT | 2022-06-01 | 1. The action does not specify what sort of information will be included. Will it just cover the catch, or will also cover ETPs, habitats and ecosystem, as well as socio-economic data? 2. A Fisheries Information System that brings together data and information about the catch for BRVT (vessel numbers, landings and fishing effort), as well as research survey results would be a good start. | 1. Revise activities with consideration of sharing existing data and access to the fishery database under jurisdiction of Fishery Directorate. Attachment: Revised FAP 2. A study about mapping fisheries information owners/sources has been conducted by TRAN Van Hao, a lecturer in Fishery Management of Nha Trang university. Attachments: the report about 'The mixed trawl fishery Data collections in Ba Ria - Vung Tau province' 3. A workshop about "Collecting multi-species fishery data and sharing data among stakeholders" was held in HCMC on August 03, 2022 in HCMC. Attachments: Participant list and invitation letter.
Action 2.1. Develop guidance for Multi-species stock assessment applicable for trawl fisheries 2.1.1 Develop guidance for ‘Multi-species stock assessment’ 2.1.2 Form the peer review committee 2.1.3 Conduct the peer review 2.1.4 Finalise the guidance document 2.1.5 Develop ToRs & contracts | 2022-06-01 | This action can benefit from existing actions that relate to similar fisheries (e.g. again see Leadbitter et al. 20xx and Kulanujaree et al. 2020. This is not a major task. | The action is completed. Attachment: 1. Interim guidance for assessing and monitoring the fish resources in the multispecies trawl fisheries of Ba Ria-Vung Tau 2. Peer review reports 3. Draft guidance, version 1 4. ToRs of the consultant and peer reviewers
Action 2.2 Multi-species stock assessment for BRVT with focus on 5 target species. 2.2.1a Design stock assessment for trawl fisheries in BRVT; 2.2.1b VN trip stock assessment for trawl fisheries in BRVT; 2.2.2 Form peer review committee 2.2.3 Conduct peer review for stock assessment framework 2.2.4 Finalise the stock assessment framework 2.2.5 Conduct stock assessment for trawl fisheries in BRVT | 2024-07-01 | The guidance document developed in Action 2.1 will probably identify that there is a number of approaches available for a multi-species stock assessment for BRVT, including aggregate production modelling, Ecopath with Ecosim (EwE) as well as an indicator species approach. The indicator species approach will need at least 10-12 indicator species (not just 5) that cover a range of risks (vulnerability to fishing) and also will be useful in assessing transboundary stocks (suggested list is available from the peer reviewer, if required). As pointed out above, there is too much emphasis on this action. | This action is partly covered by Action 2.1 and will be combined with Action 2.3, hence Action 2.2 is removed and won't appear in the revised FAP. Attachment: Revised FAP
Action 2.3: Collect data of BRVT Trawl fisheries 2.3.1 Design for upgrade trawl fisheries data collection system that can provide correct information about species caught and land, species omposition, CPUE and other fishing effort data; 2.3.2 Introduce the upgrade to DARD and sub-DOF of BRVT and propose for pilot application; 2.3.3 Pilot with some trawl fleets that registre with BRVT authorities; 2.3.4 Analyse data; 2.3.5 Hold workshops to share with stakeholders about pilot results and discuss for expansion of application to all trawl fleets under BRVT administration; 2.3.6 Present to BRVT People's Committee and DARD; 2.3.7 Follow up | 2024-04-01 | This needs to build on the existing system of fisheries data collection that already exists at the provincial/district level. A review of the methodology and what data are currently collected would be a first step for an upgrade. This should link to Action 1.2 to make any new information available. | 1. Revise the goal of the action to improve the quality of data collected for BRVT trawl fisheries. 2. Revise activities. Attachment: Revised FAP
Action 2.4: Develop BRVT ETP species database 2.4.1 Revise fishing logbook for trawl fisheries that enable record ETP species caught; 2.4.2 Introduce the new logbook to sub-DOF of BRVT and propose for pilot application; 2.4.3 Pilot with some trawl fleets that registre with BRVT authorities; 2.4.4 Conduct landing site inspections of BRVT trawl vessels and check for ETP species landings; 2.4.5 Analyse data and revise (if necessary); 2.4.6 Hold workshops to share with stakeholders about pilot results and discuss for expansion of application to all trawl fleets under BRVT administration; 2.4.7 Present to BRVT People's Committee and DARD; 2.4.8 Follow up. | 2024-04-01 | This action aims to bring together a lot of existing information (this needs to include CITES) and compare this with logbook data. This is an important action, but could be difficult to achieve using logbooks. Fishers are going to be reluctant to record interactions with ETPs if they perceive any consequences. Observers could be a better option (or at least in conjunction with logbooks). | 1. Combine with Action 2.5 and Action 2.6 2. Revise the goal of the new action to assess the status of the fishery resource and develop management measures as inputs into the development of the FMP. 2. Rewrite activities. Attachment: Revised FAP
Action 2.5: Conduct assessment about impacts of trawl fisheries on ETP species in BRVT. 2.5.1 Conduct an assessment about the interaction of BRVT trawl fisheries with ETP species, including observation on board fishing vessel; 2.5.2 Introduce the assessment results to stakeholders and have their consultation for proposed impact limits on ETP species. | 2023-04-01 | This action follows on from Action 2.4 and should lead to mitigation limits. This should include methods and techniques to return ETPs live back to the sea in case of incidental capture. As outlined in Action 1.1, any management measures that arise from this work should be integrated into the new Fisheries Management Plan. | 1. Combine with Action 2.4 and Action 2.6 2. Revise the goal of the new action to assess the impact of the trawl fishery on ETPs and develop mitigation measures as inputs into the development of the FMP. 2. Rewrite activities. Attachment: Revised FAP
Action 2.6: Collecting information relating to at-sea garbage disposal and gear loss/retrieval, and associated ghost fishing. 2.6.1 Scientific desk review about the nature, distribution and vulnerability of the commonly encountered habitats in waters under BRVT administration; 2.6.2 Develop information collecting system for at-sea garbage disposal and gear loss/retrieval, and associated ghost fishing; 2.6.3 Introduce to sub-DOF of BRVT; 2.6.4 Collect data; 2.6.5 Analyse data; 2.6.6 Present to BRVT People's Committee and DARD. | 2024-07-01 | This action seems to combine direct impacts of the vessels with critical habitats and indirect effects caused by at-sea garbage disposal, gear loss/retrieval and associated ghost fishing, but this not clear. The links to action 2.7 are also not clear (2.7 also covers ghost fishing, at-sea garbage disposal and gear loss/retrieval). | 1. Combine with Action 2.4 and Action 2.5 2. Revise the goal of the new action to assess the impact of the trawl fishery on ETPs and develop mitigation measures as inputs into the development of the FMP. 2. Rewrite activities. Attachment: Revised FAP
Action 2.7: Conduct a study about Vulnerable Marine Ecosystems (VMEs) within the waters under the administrative management of BRVT province. 2.7.1 Conduct a study about Vulnerable Marine Ecosystems (VMEs) within the waters under the administrative management of BRVT province; 2.7.2 Present the study's results to DARD and the sub-DOF of BRVT. | 2024-07-01 | This action needs a better definition of Vulnerable Marine Ecosystems (VMEs). As mentioned, most of the traditional trawling grounds are flat muddy and sandy bottoms. Are these VMEs? The MarinTrust assessment specifies “critical habitats” i.e. A habitat that is essential to maintaining the integrity of an ecosystem, species or assemblages of species. For a species, it is the habitat that is important for the spawning and survival of juvenile fish, which if degraded, results in a decline the abundance of fish. | Remove this Action from FAP. Attachment: Revised FAP
Action 2.8: Develop habitat management plan for BRVT. 2.8.1 Develop habitat management plan; 2.8.2 Hold consultation workshops with stakeholders; 2.8.3 Present final plan to DARD and the sub-DOF of BRVT and support for implementation. | 2023-04-01 | This needs to be integrated into the Fisheries Management Plan, in line with EAF. If this is likely to delay the development and implementation of a Fisheries Management Plan, then a separate plan as a transitory step may be needed. Also, it is probable that habitat management plans already exist for Vietnam, and these need to be built on. | 1. Revise the goal of the action to assess the impact of the trawl fishery on critical habitats and develop mitigation measures as inputs into the development of the FMP. 2. Revise activities. Attachment: Revised FAP
Action 2.9: Conduct a study about the key ecosystem elements of the UoA. 2.9.1 Conduct a study about the key ecosystem elements of the UoA; 2.9.2 Present the study's results to DARD and the sub-DOF of BRVT. | 2023-04-01 | Identifying key ecosystem elements will include ecosystem modelling. Ecosim with Ecopath (EwE) models exist for similar ecosystems (e.g. Thai waters in the Gulf of Thailand and southwest Vietnam (again see Leadbitter et al. 20xx) These could assist in completing Action 2.9. | 1. Combine with Action 2.10 and Action 2.11 2. Revise the goal of the new action to assess the impacts of the BRVT fishery of the structure and function of the ecosystem in BRVT and develop mitigation measures as input into the FMP 2. Rewrite activities. Attachment: Revised FAP
Action 2.10: Conduct studies on status and changes of demersal resources with impacts of trawl fisheries. 2.10.1 Conduct a desk study to review and analysis the available historical trawl survey data in BRVT; 2.10.2 Present the study's results to DARD and the sub-DOF of BRVT. | 2023-04-01 | As well as a review of past trawl survey data, this action could include ecosystem modelling. As also note above Ecosim with Ecopath (EwE) models exist for similar ecosystems. | 1. Combine with Action 2.9 and Action 2.11 2. Revise the goal of the new action to assess the impacts of the BRVT fishery of the structure and function of the ecosystem in BRVT and develop mitigation measures as input into the FMP 2. Rewrite activities. Attachment: Revised FAP
Action 2.11: Develop ecosystem management plan for the UoA. 2.11.1 Develop ecosystem management plan; 2.11.2 Hold consultation workshops with stakeholders; 2.11.3 Present final plan to DARD and the sub-DOF of BRVT and support for implementation. | 2023-04-01 | This also needs to be integrated into the Fisheries Management Plan, in line with EAF. If this is likely to delay the development and implementation of a Fisheries Management Plan, then a separate plan as a transitory step may be needed. | 1. Combine with Action 2.9 and Action 2.10 2. Revise the goal of the new action to assess the impacts of the BRVT fishery of the structure and function of the ecosystem in BRVT and develop mitigation measures as input into the FMP 2. Rewrite activities. Attachment: Revised FAP
Action 2.12: Project management 2.12.1 Develop ToRs & contracts 2.12.2 Organize workshops, conferences, meetings 2.12.3 Administration and payments | 2024-12-01 | Obviously essential. However, the estimated cost seems to be very high (18.1% of the total budget). | 1. Review project management activities and keep the budget unchanged. 2. ToRs and contracts have been developed, implemented for Action 2.1 3. A FIP partner meeting to update progress of first six months of 2022 was held in Vung Tau on July 29, 2022. 4. A field trip to visit FIP fishmeal members was held on July 30, 2022 5. A workshop about data collection and sharing was held in HCMC on August 01, 2022 Attachment: 1. ToRs and Contracts for Fish Matter, TRAN Van Hao, TRAN Dac Dinh and Derek Staples 2. FIP partner meeting presentation and photo 3. Photo of the field trip 4. Presentation and photo of the workshop

## Revised FAP
Items | Descriptions | Deliverable | Start date | End date
Action 1.1 | Fisheries management plan (FMP) for the trawl fishery in BRVT |  | 2022-01-01 | 2024-12-01
Objective: | Develop a Fisheries Management Plan (FMP) through a co-management approach
Gap addressed: | M1.7
Justification: | No fisheries management plan (FMP) for the trawl fishery of BRVT No specific goals and objectives No allocation of roles and responsibility for managemen
Action Description: | 1.1.1: Review of current trawl fishery management policies, objectives (including Master plan objectives) and management measures in place in BVRT | A report about current trawl fishery management policies, objectives (including Master plan objectives) and management measures in place in BVRT | 2022-01-01 | 2023-12-01
| 1.1.2 Form key stakeholder team and lead agency (co-management). Stakeholder team to consult more widely with stakeholders during FMP development | Team agreement | 2023-01-01 | 2023-02-01
| 1.1.3 Key stakeholder team agree on need, scope and overall policy goals for the FMP. Fishery resources, ETPs, critical habitats, ecosystem, compliance and enforcement Prepare outline for the proposed FMP. | FMP headings and outline | 2023-01-01 | 2023-02-01
| 1.1.4 Develop a workplan on actions needed to develop a FMP that links with all of the other FAP actions (e.g. status assessments etc) | Workplan | 2023-01-01 | 2023-02-01
| 1.1.5 Conduct stakeholder workshop(s) Stock status: Discuss results of stock assessments; Agree on management measures to control catches ETPs: Discuss results of the review of interactions with ETPS; Agree on methods to mitigate ETP interactions; Agree on methods to record future ETP interactions Habitats: Discuss results of impact studies on critical habitats; Agree on methods to mitigate impact; Agree on data collection for future monitoring Ecosystems | Workshop reports | 2023-01-01 | 2023-02-01
| 1.1.6 Input results into the draft FMP | Draft FMP | 2023-11-01 | 2023-12-01
| 1.1.7 Share the draft FMP with the Sub-DOF BRVT and prepare to get endorsement and adoption by Sub-DOF BRVT at provincial level | Consultation reports | 2023-12-01 | 2023-12-01
Priority | Very high
Estimated Cost | 64.000 USD
Responsible Parties | Fish matter Pty Ltd Directorate of Fisheries of Vietnam DARD BRVT Sub-DOF BRVT Nha Trang University / Institute for Marine Science & Fishing Technology Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Kim Delta Vietnam
Action 1.2: | Mechanism for fisheries information sharing with DARD, Sub-DOF BRVT and BRVT Port authorities. |  | 2022-08-01 | 2022-12-01
Objective: | Support BRVT authorities for better management of trawl fisheries activities in the province.
Gap addressed: | M1.7, M3.3 and M3.5
Justification: | Ineffective co-management and coordination mechanisms among stakeholders Ineffective compliance and enforcement (MCS), including sharing of information on illegal, unregulated and unreported fishing (IUU)
Action Description | 1.2.1: Map existing fisheries information owners and sources of data among stakeholders | Report | 2022-08-01 | 2022-12-01
| 1.2.2 Assess the current mechanisms for sharing data and information | Report | 2022-08-02 | 2022-12-02
| 1.2.3: Key stakeholder workshop to agree on what data and information needs to be shared (e.g. vessel data, catch data, IUU data etc) and agree on the best mechanism for sharing (e.g. expand existing databases, open access portal etc) | Workshop report | 2022-10-01 | 2022-10-01
| 1.2.4 Develop mechanisms for sharing of data and information | A portal to publish trawl fishery data / information | 2022-10-01 | 2022-12-02
Priority | High
Estimated Cost | 20.000 USD
Responsible Parties | Nha Trang University / Institute for Marine Science & Fishing Technology Vung Tau RIMF DARD BRVT Sub-DOF BRVT Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Landing port authorities Kim Delta Vietnam
Action 2.1: | Collection of trawl fisheries data |  | 2022-08-01 | 2023-12-01
Objective: | Improve the quality of data collected for BRVT trawl fisheries
Gap addressed: | A2,B2,C2: Expected rating from High risk to Medium risk
Justification: | Data of total landings from fisheries, CPUE, species composition and catch composition are not available at species level.
Action Description | 2.1.1 Review existing systems and identify gaps | Report | 2022-08-01 | 2022-12-01
| 2.1.2 Conduct workshop with key stakeholders to agree on how to upgrade existing systems | Workshop Report | 2022-10-01 | 2022-10-01
| 2.1.3 Trial the upgrade with selected vessels and DARD/Sub-DOF cooperation | Report | 2022-10-01 | 2022-12-01
| 2.1.4 Mainstream the improvement through DARD/Sub-DOF | New system | 2023-01-01 | 2023-12-01
Priority | High
Estimated Cost | 20.000 USD
Responsible Parties | Nha Trang University / Institute for Marine Science & Fishing Technology Vung Tau RIMF DARD BRVT Sub-DOF BRVT Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Fish Matter Pty Ltd Kim Delta Vietnam
Action 2.2: | Status and management of fisheries fishery resources |  | 2022-08-01 | 2023-12-01
Objective: | Assess the status of the fishery resource and develop management measures as inputs into the development of the FMP.
Gap addressed: | A3-A6 and B3-B6: Expected rating from High risk to Medium risk
Justification: | The status of the fishery resource is known with a low degree of certainty The status of high-risk species is unknown. No management measures have been developed.
Action Description | 2.2.1 Review the range of single-species and multi-species stock assessment methods that could be used in the BRVT trawl fishery, based on existing and possible new data | Report | 2022-08-01 | 2022-12-01
| 2.2.2 Critically review the existing single-species and multi-species stock assessments related to the BRVT trawl fishery | Report | 2022-08-01 | 2022-12-01
| 2.2.3 Conduct workshop to identify gaps in the assessments and agree on: - the groups to be used aggregated assessment methods - a set of set of indicator species based on a PSA analyses (high risk, medium risk and low risk species) that will be used to guide management (need 10-15 species, not just 5) - how to assess the impact on juvenile fish of high-value species - target reference point (TRP) for the aggregate catch and limit reference point(s) (LRP) for the high-risk/vulnerable species | Workshop Report | 2023-02-01 | 2023-02-01
| 2.2.4 Conduct additional analyses deemed necessary | Stock assessment Reports | 2023-02-01 | 2023-12-01
| 2.2.5 Prepare results for input into stakeholder consultations and development of the FMP. | Powerpoint presentation | 2023-07-01 | 2023-07-01
Priority | High
Estimated Cost | 30.000 USD
Responsible Parties | Central RIMF Nha Trang University / Institute for Marine Science & Fishing Technology DARD BRVT Sub-DOF BRVT Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Consultant Kim Delta
Action 2.3: | Status and management of the reduction component of the catch. |  | 2022-08-01 | 2023-07-01
Objective: | Assess the status of the reduction component of the catch and develop management measures as inputs into the development of the FMP.
Gap addressed: | C2-C6: Expected rating from High risk to Medium risk
Justification: | Insufficient data and information concerning the reduction component of the catch The status of the reduction component is unknown. No management measures have been developed.
Action Description | 2.3.1 Based on sampling, determine the species composition of the reduction component of the catch in four categories: “by-products”, “true trash fish”, “poor quality high-value fish” and “juveniles of high-value fish”. | Report | 2022-08-01 | 2022-12-01
| 2.3.2 Assess the status of the different categories of the reduction component of the catch for (i) aggregate by-product fish (ii) aggregate trash fish catch and (iii) stock assessments/risk assessments for indicator species. | Stock assessment report | 2023-01-01 | 2023-07-01
| 2.3.3 Develop a monitoring program for tracking the species composition of the reduction catch, at annual intervals. | Annual report | 2023-01-01 | 2024-12-01
| 2.3.4 Prepare results for input into stakeholder consultations and development of the FMP. | Powerpoint presentation | 2023-07-01 | 2023-07-01
Priority | High
Estimated Cost | 30.000 USD
Responsible Parties | Central RIMF Nha Trang University / Institute for Marine Science & Fishing Technology DARD BRVT Sub-DOF BRVT Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Consultant Kim Delta
Action 2.4: | Status and management of ETPs |  | 2023-01-01 | 2023-07-01
Objective: | Assess the impact of the trawl fishery on ETPs and develop mitigation measures as inputs into the development of the FMP
Gap addressed: | T1-T3: Expected rating from High risk to Medium risk
Justification: | A comprehensive study about the interaction/effects of the trawl fishery with/on ETP in BRVT waters is not conducted yet.
Action Description | 2.4.1 Develop a list of ETPs for the BRVT based on IUCN,CITES, national lists etc | Report | 2023-01-01 | 2023-07-01
| 2.4.2 Review information on interactions of BVRT trawlers with ETPs - Observer data - Interviews with fishers - Landing site inspections of BVRT trawl vessels and check for ETP landings | Report | 2023-01-01 | 2023-07-01
| 2.4.3 Conduct risk-based assessment of the impact of trawling on ETPs - Direct impact of trawling - Indirect impact lost gear | Report | 2023-01-01 | 2023-07-01
| 2.4.3 Prepare results for input into stakeholder consultations and development of the FMP. | Powerpoint presentation | 2023-07-01 | 2023-07-01
Priority | Moderate
Estimated Cost | 15.000 USD
Responsible Parties | Nha Trang University / Institute for Marine Science & Fishing Technology DARD BRVT Sub-DOF BRVT Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Kim Delta Vietnam
Action 2.5: | Status and management of critical habitats. |  | 2023-01-01 | 2023-07-01
Objective: | Assess the impact of the trawl fishery on critical habitats and develop mitigation measures as inputs into the development of the FMP.
Gap addressed: | H1-H3: Expected rating from High risk to Medium risk
Justification: | A comprehensive study about the nature, distribution and vulnerability of the commonly encountered habitats in BRVT waters is not conducted yet. There are no scientific studies to evaluate interaction.
Action Description | 2.5.1 Scientific desk review about the nature, distribution and vulnerability of the commonly encountered critical habitats in BRVT Include baselines of past distribution and habitat quality | Report | 2023-01-01 | 2023-07-01
| 2.5.2 Conduct risk-based assessment of the impact of trawling on critical habitats - Direct impact of trawling - Indirect impact lost gear | Report | 2023-01-02 | 2023-07-02
| 2.5.3 Prepare results for input into stakeholder consultations and development of the FMP | Powerpoint presentation | 2023-07-01 | 2023-07-01
Priority | Moderate
Estimated Cost | 15.000 USD
Responsible Parties | Nha Trang University / Institute for Marine Science & Fishing Technology DARD BRVT Sub-DOF BRVT Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Kim Delta Vietnam
Action 2.6: | Status and management of ecosystem structure and function |  | 2023-01-02 | 2023-07-02
Objective: | Assess the impacts of the BRVT fishery of the structure and function of the ecosystem in BRVT and develop mitigation measures as input into the FMP
Gap addressed: | E1-E3: Expected rating from High risk to Medium risk
Justification: | There is no information to identify the ecosystem elements in BRVT waters, hence main impacts of the trawl fishery on these key ecosystem elements cannot be inferred.
Action Description | 2.6.1 Scientific desk review on the changes in the ecosystem structure (species composition) based on historic research trawl surveys | Report | 2023-01-01 | 2023-07-01
| 2.6.2 Review and describe any existing ecosystem models (e.g. Ecopath with Ecosim) that could be used to model the ecosystem dynamics of the BRVT marine ecosystem. | Report | 2023-01-02 | 2023-07-02
| 2.6.3 Prepare results for input into stakeholder consultations and development of the FMP | Powerpoint presentation | 2023-07-01 | 2023-07-01
Priority | Moderate
Estimated Cost | 10.000 USD
Responsible Parties | Nha Trang University / Institute for Marine Science & Fishing Technology DARD BRVT Sub-DOF BRVT Fishery Association of BRVT Fishmeal & Fish Oil Association of BRVT Kim Delta Vietnam
Action 2.7: | Project Management |  | 2022-01-01 | 2024-12-01
Objective: | Ensure that all actions covered by this action plan are executed and achieve its goals within the agreed timeframe and budget.
Gap addressed: | Not applicable
Justification: | Not applicable
Action Description | 2.7.1 Develop ToRs & contracts 2.7.2 Organize workshops, conferences, meetings 2.7.3 Engage advisors at critical steps in the project 2.7.3 Administration and payments |  | 2022-01-01 | 2024-12-01
Priority | High
Estimated Cost | 45.000 USD
Responsible Parties | Kim Delta Vietnam