## Sheet1
IOS FIP Workplan – January 2023 revision
Table 2 – proposed Actions to close the gaps
Proposed Actions – stock assessment | Outputs | Year start | Year End | Time budget | Lead responsibility | Days budgeted | Progress | Audit trace | 2024
Gaps addressedA1.2, A2.1-A2.5
Data collecting program based on results of workshop. Investigate alternative data collection approaches if stock assessment cycle cannot be changed by government. | Fishery management plans |  |  | 10 months | Fisheries agency management staff, CMFRI | 5 days FIP consultant, 10 days local consultant | Research report complete. Next phase is to discuss ongoing data collection | Report | FIP to seek agreement that stock assessment cycle to be committed in management plans (Goa and Maharashta
Proposed Actions – harvest strategy | Outputs | Time Table |  | Time budget | Lead responsibility | Days budgeted
Gaps addressedA3.1-A3.3
Establish reference points for the sardine stock based on best practice. | Fishery management plans |  |  | 10 months | Fisheries agency management staff, CMFRI | 5 days FIP consultant 10 days local consultant | Workshop has been completed. Report sent to MT and loaded on to website (June 2022 | Workshop report | FIP to seek agreement that Reference Points to be included in management plans (Goa and Maharashta)
Establish harvest control rules for each sector - There are two sectors for harvest control. ie., Purse seine/ shore seine |  |  |  | 10 months | Fisheries agency management staff, CMFRI | 10 days local consultant 5 days FIP consultant
| Fishery management plans | [5 empty] | Workshop has been completed. Report sent to MT and loaded on to website (June 2022 | Workshop report | FIP to seek agreement that HCRs for purse seine sector to be included in management plans (Goa and Maharashta
Proposed Actions – Monitoring, Control and Surveillance | Outputs | Time Table |  | Time budget | Lead responsibility | Days budgeted
Gaps addressedM2.1, M2.3, M2.4
Document how MCS efforts work towards implementation of national policy | Report |  |  | 1 months | MCS Consultant and agency staff | 1 day FIP consultant 1 day local consultant | Completed January 2023 | Report submitted to Marin Trust | To be updated December 2023
Proposed Actions – ecosystem impacts | Outputs | Time Table |  | Time budget | Lead responsibility | Days budgeted
Gaps addressedF3.1-F3.3
Update and extend current Ecosim with Ecopath (EwE) model for SW India. Include climate change effects and effects of predators such as dolphins | Report | .December 2023 | .October 2024 | 1 months | Science agency staff | 10 days EwE consultant 5 days local consultant | Literature obtained and discussions held with scientists on the way forward. A brief overview of what is required has been prepared to assist the discussions | Literature and email correspondence | Interim report end December 2023.
Model and evaluate the effects of the fishery of interest and other sardine fisheries. Workshop with stakeholders | Report | .March 2024 | .October 2024 | 3 months | Science agency staff |  | To be undertaken once EwE model is prepared |  | Final model available end March 2024
Incorporate any of the important results of the modelling into the fishery planning. | Fishery management plans | .January 2024 | .October 2024 | 10 months | Fisheries management staff and stakeholders | 10 days FIP consultant 5 days local consultant |  |  | FIP to seek agreement that any relevant model implications to be included in management plans (Goa and Maharashta)
Discussions with agency about fishery planning (i.e. management plan preparations | Fishery management plans | .January 2024 | .October 2024 | 10 months | Fisheries management staff and stakeholders | 20 days local consultant 10 days FIP consultant |  |  | FIP team to follow up letters received from Goa and Maharashtra fisheries agency confirming their support for the development of fisheries management plans
Discussions with agency about fishery planning (i.e. management plan preparations | Fishery management plans | .January 2024 | .October 2024 | 2 months | FIP team, government agency staff and stakeholders | 10 days fIP consultant 10 days local consultant |  |  | Workshop on fishery management planning to be held with follow up meetings with agency staff to discuss implementation options (regulatory/policy) and timetable
Discussions with agency about fishery planning (i.e. management plan preparations | Fishery management plans | .January 2024 | .October 2024 | 10 months | FIP team, government agency staff and stakeholders | 7 days fIP consultant 10 days local consultant |  |  | Monthly calls to government agencies check on progress on management plan development. Monthly internal FIP team calls and monthly stakeholder updates
Discussions with agency about fishery planning (i.e. management plan preparations | Fishery management plans | .January 2024 | .October 2024 | 10 months | FIP team, government agency staff and stakeholders | 7 days fIP consultant 10 days local consultant |  |  | Ensure that stakeholders are kept updated via regular emails/calls. One in-person stakeholder workshop to be held at least one month before October 2024